| الموضوع/ المشروع | Marketing Kickoff – Ramadan Campaign | النوع | اجتماع متابعة أسبوعي |
| --- | --- | --- | --- |
| الإدارة المعنية |  | التاريخ | 6/1/1448 هـ الموافق 2026-06-21م |
| الجهة الطالبة للاجتماع | مكتب إدارة البيانات | الوقت | 1:00 مساءً – 2:00 مساءً |
| ميسّر الاجتماع |  | المدّة | ساعة من 14:00 – 13:00 |
| معد من قبل | عهد القحطاني | المكان | in-person |

| الحضور |  |
| --- | --- |
| المنصب | الاسم |
| Meeting Chair | Layla |
|  | Hajji Omar |
| Chief Data Management Officer | Adel AlHarbi |
|  | Mira |

الهدف من الاجتماع

Kick off the marketing planning for the Ramadan campaign, review creative concepts, and align on budget and influencer strategy

نقاط النقاش الرئيسية

1. Khalid presented three creative concepts for the Ramadan campaign; the team evaluated and discussed the merits of each. 2. The second creative concept — the storytelling angle — was selected as the preferred direction. 3. Layla raised the concern that budget approval from upper management has not yet been obtained, which could impact timelines. 4. Hajji Omar committed to escalating the budget request to the board for approval this week. 5. The team discussed the influencer strategy and the need to finalize a shortlist of influencers for the campaign. 6. Mira was tasked with shortlisting five influencer names to share before the next meeting. 7. The tentative campaign launch is planned for the first week of Ramadan, though the timeline is tight and contingent on budget clearance. 8. The team acknowledged the need to confirm the launch date once the budget is approved.

| الحالة | تاريخ الاستحقاق | المسؤول | المهام والأعمال المتفق عليها | # |
| --- | --- | --- | --- | --- |
|  | 2026-06-24 | Eng. Khalid Al-Dosari | Send over final mockups for the selected storytelling creative concept |  |
|  | 2026-06-27 | Hajji Omar | Escalate budget request to the board and obtain approval or rejection |  |
|  | 2026-06-25 | Mira | Shortlist five influencer names and share with the team before the next meeting |  |
|  |  |  | Confirm campaign launch date once budget is cleared |  |